Targeting in VR
Study design document

Purpose of study (Research hypothesis)
Participants try to shoot on a target which has different distances to the participants with a controller. They try to shoot with a crosshair, a laser beam, and both crosshair and laser beam.
The further away the target, the bigger the error rate and the more time the participants need.
Beam could actually disturb the participants; crosshair should be good enough for aiming.
Participant profile
Students from University Stuttgart
Methodology

Variables:
Independent variables	Dependent variables
Distance (5,10,15m)	Time they need
Different laser types	Error rate
Distance between targets	Precision
(Posture)

Timeline
Timeline of each task:
Subject	Time
Study design	1st week
Implementation (Visualization)	1st week
Implementation (Visualization)	2nd week
Implementation (distance and time)	2nd week
Implementation (distance and time)	3rd week
Testing	Before Christmas
Questionnaires	Before Christmas

Timeline of experiment:
Hour	Day 1: 12.01.2017			Day 2: 16.01.2017

Method of analysis
After the participants took part at the study they will be asked to fill out a questionnaire on the computer. We will analyze the results and make charts out of it.
Resources to be acquired/prepared
Computer, VR-Glasses, Controller, Room, People of the team, questionnaires, Kinder Rigel for a little Thank You.
Course of Study
Medieninformatik, Maschinelle Sprachverarbeitung
Personnel Involved
Mischa Rippel, Ebru Güner, Emine Turcan, Ralitsa Todorova, Olga Stroh, Sara Darwish, Kevin Wennrich